## Sheet1
| Project Name | NEW IN-HOUSE iCARD IMPLEMENTATION
| Project Manager | ADEPOJU SODIQ
| Project Deliverable | iCARD
Start Date
End Date
| Overall Progress | 21.43%
S/N | Tasks | Responsible | Priority | Estimation | Start | End | External Dependencies | Status
1 | Provide information on the bank's backend systems to integrate to - KYC Retrieval Service (CBA) - Transaction Posting Service (CBA) - Card Management Systems (In-House/Out-of-Premise) - HSM - Active Directory - Mail Server - SMS Gateway | Pajuno | 1 |  |  |  |  | Complete | 1
2 | Provide Information/documentation on integrations with Gemalto | Pajuno | 1 | [5 empty] | 0
3 | Provide Documentation on process flows, modules, functionality etc | Pajuno | 1 |  |  |  |  | Complete | 1
4 | Provide sufficient explanations of these documents to ensure all parties are in sync | Pajuno | 1 |  |  |  |  | Complete | 1
5 | Define Scope of work | Pajuno/Mr Festus | 1 | [5 empty] | 0
6 | Commence Backend Implementation | Mr Festus/Software Team | 2 | [5 empty] | 0
7 | Develop wireframes for the front-end design | Pajuno | 2 | [5 empty] | 0
8 | Commence Front-end implementation | Software Team | 2 | [5 empty] | 0
9 | Integration Testing with Gemalto - Create Card Requests - Produce Cards (in conjunction with satellites) | Mr Festus/Pajuno | 3 | [5 empty] | 0
10 | Acceptance Testing (of functionality) with Pajuno | Mr Festus/Pajuno | 3 | [5 empty] | 0
11 | End-To-End Testing | Mr Festus/Pajuno | 3 | [5 empty] | 0
12 | Security Testing | Mr Festus/Pajuno | 3 | [5 empty] | 0
13 | Stress Testing on Accepted Solution | Mr Festus/Pajuno | 3 | [5 empty] | 0
14 | Formal Solution Acceptance | Mr Festus/Pajuno | 3 | [5 empty] | 0
3
S/N | Tasks Performed |  |  |  | Start | End